## Sheet1
Activity | Person | Date | Activity | Steps and Directions
Budget | Scholarship committee | Fall, preceding | Request funding for 8 scholarships from PHISIM board | Discuss with PHISIM board the number of scholarships that are expected to be presented for upcoming year and the amount to be awarded.
| Scholarship Comittee | December, preceding year | Review the processing dates for the process based on the presentation set for the April dinner meeting date | Update the dates for the scholarship process to finish with awards presented at the April Dinner meeting. The template for the processing is in the next link. Then create a formal document to be used for the process which will be part of communications with academic members and student nominees.
Academic Members | Scholarship committee | January of current scholarship funding | Request list of academic members from Philadelphia SIM chapter administrator, Maureen Waddington, admin@simphila.org | Get the list of all SIM members who are from Academic Institutions. The expectation is that dues will be current for the upcoming year.
|  |  | Sort list for faculty members, removing administrative IT members | Review the list of current SIM members from Academic institutions. Update the list include only curent academic SIM members who are full time faculty at the instution.
|  |  | Compare list of faculty members to previous years | Review the current list of academic SIM members list from this year with the list from the previous year. Update the list to be sure all current members are included.
|  |  | Contact any faculty members who did not renew to current year | If a member from the previous year is not on the current year, contact the member to see if they intend to extend the SIM membership. If the member does not extend the membership, the member is not able to submit a candidate for the PHISIM scholarship. If another academic member of that school and department from the school is a current SIM member, that member may become the member to nominate the candidate from the school/department.
Qualify/re-qualify universities | Scholarship committee | 2025-01-12 | Review tracking chart for university re-qualification | Review the list of schools who are eligible for scholarships based on an academic member being a current SIM member for the current year AND the academic qualifications have been reviewed over the past 3 years. The worksheet if reviewed every year to decide the schools which need to be requalified as well as the addition of any new schools for the list. A school can only have ONE nomination per department/school. If more than multiple academic members from the same school but different departments are current/active members of SIM, both departments are eligible to be reviewed for qualificaiton and submission of a scholarhship candidate. For example, Temple had a current academic SIM member in the School of Arts/CSC department and the Business School/MIS department. Both schools/departments may be qualified and if accepted, each department may submit a name for a scholarhship candidate. The spreadsheet that is reviewed is listed in the next column.
|  |  | Send letter of re-qualification to universities | Schools that are eligible to submit scholarship candidates must be "qualified" according to the PHISIM requirements. Schools need to requalify every 3 years. Based on the results from the spreadsheet list from the previous step, the school current academic SIM members are sent letters to request documentation for the requalification. A sample of the letter is listed in the link in the next column. The information sent for qualification includes the cover letter, the process timeline and the qualification form. | Qualification Document Template to be completed by schools that need to requalify: https://docs.google.com/document/d/10n1pR8sIKZrItK7bxK0ldcqvwNv9CUFQ/edit?usp=sharing&ouid=104579106202079848051&rtpof=true&sd=true
| Board members | 2025-01-26 | Review the re-qualification applications | Review the submitted qualification documents and update the requalification spreadsheet with the information from submitted by the institution. Submit the request to PHISIM board members to approve the University. Note the updates in the spreadsheet.
| Scholarship committee | 2024-01-26 | Send appropriate letter to universities seeking re-qualification | If an academic institution needed to be requalified and it is approved by the PHISIM Board, send a letter to the Academic SIM member for the institution that the university has been approved to participate in the nomination.
Invite student nominations for universities | Scholarship committee chair | 2024-01-12 | Send student nomination letter to universities which do not need to be requalified | Prepare a letter for each SIM Academic Member from the approved institutions to nominate a student for the current year scholarship. The letter includes the template, the process timeline and the student nomination approval template. | Student Nomination Form https://docs.google.com/document/d/1Zck0ySopQyTm3WRErMV7lPfDBQz--Uxb/edit
|  | 2024-01-26 | Send student nomination letter to universities which were reviewed and requalified | Update the spreadsheet with the list of student nominees.
Obtain student plaques | Scholarship committee chair and Chapter Administrator | 2024-02-09 | Chair sends students' names and universities to chapter administrator who will order the plaques | Using the list of nominees send the list to Administrator to print the plaques
|  | 2024-02-29 | Review draft text on student plaques | Review the list submitted by the administrator
Notify students of awards | Scholarship committee chair | 2024-02-09 | Send award letters to students with copy to faculty | Send the award letters to the students and faculty advisors. You need to include the student ID numbers for students at Temple and Drexel | Student Form: hhttps://docs.google.com/document/d/1OVFCrWaIJFCwajyXI1XiI7EmyQPdidqx/edit
Obtain student plaques | Scholarship committee chair | 2024-02-09 | Inform SIM chapter administrator of students' names and universities for plaques | CHeck on Plaque status
Obtain testimonials from past recipients | Scholarship committee chair | 2024-02-19 | Send request for testimonial and photo letters to past recipients | Contact former recepients request testimonial on current status and photo if available. Update the list to include the nominees for the current year.
Create recognition presentation | Scholarship committee chair | 2024-02-23 | Create powerpoint presentation | Create the presentation for the April Dinner based on the current and past awardee submissions. You may need to ask each academic member for a short speech about the nominee to be used in the presentation and at the award ceremony
Board review of presentation
Establish photograph list | Scholarship committee chair | 2024-03-09 | Create list of groups to be photographed: student+faculty+president; group of all students, president, committee
Conduct recognition ceremony | Scholarship committee chair | 2024-04-02 | Deliver presentation at SIM chapter event | April Dinner Event includes presentation OR short description for each awardee.
Send checks to schools | PHISIM Treasurer | May | Send a list of the awardees, the addresses and needed information to the Treasure to issue the scholarship Checks. Generate the letter for the Treasurer to include with the checks.